## Slide 1: Electronic Marking System
Shaimaa Hossam
Sohila Noaman
Nour Mostafa
Mennatallah Mostafa
Nada MoheyEldin
Haneen Hamada

## Slide 2: Project content
Project Charter
Scope Statement
Work Breakdown Structure
Responsibility Matrix
Network
Gantt Chart
Resource Constrained Schedule
Time-Phased Budget
Risks

## Slide 3
Project Name | Electronic Marking System |  | 
Project Sponsor | The Government | Project Manager | Sohila Noaman
Date Of Project Approval | 3 Sep 2021 | Last Revision Date | 30 Oct 2021
Project Description | It is the possibility to mark an exam automatically and return within a very short period of time using computers, As the students submit their form via internet so that their answers are marked and the results are returned automatically. |  | 
Scope | The project is aimed to solve the predicament of wasting time on correcting exams. The solution we reached is a marking exam that will have the following benefits: Less time wasted Fair and faster correction The marking system requires certain rules: The exam must be multiple choice question only The exam must be tested on computers The project inly works on windows The drawbacks of the system: Lack of equipment required in schools Lack of experience with this type of technology Out of the scope: Linux computers Essay exams |  | 

## Slide 4
Project Purpose | The major aim of this project is to develop a marking system that would be capable of providing on accurate marks very fast for thousands of forms. | 
Constraints (In priority order) | Time | 3 months
 | Budget | 10 developers + 10 PCs
Project Deliverables | By the end of the project, we will be able to create a powerful system capable of correcting all exams electronically. This system will save a lot of time and effort in correcting exams Keeping pace with the age of technology | 
Benefits | Saves time and speeds up the process of correcting the exams. Secure, Environment-friendly. Reducing the risk of human mistakes and the risk of exam papers being lost. | 
Steering Committee | Executives CEO Senior stakeholders Sales director Experts Finance director | 
Key Stakeholders | Government Owners Sponsors Partners Suppliers Managers | 

## Slide 5
Risks | The risks of this project are also considered to avoid any problems and try to solve them fast, And the risks are: The lack of sufficient experience to deal with the modern technology that is used in the project. The delay of some schools or universities in terms of technology makes them unable to implement the project. Some failures occur in the system or in the network.

## Slide 6: Scope Statement

## Slide 7
The major aim of this project is to develop a marking system that would be capable of providing an accurate marks as fast as possible for thousands of forms.
Scope Statement
This project will be done within 3 months.
Constraints
-Budget: 10 developers + 10 PCs
-Time constrained.
The project is aimed to solve the predicament of wasting time on correcting exams, The solution we reached is an electronic marking system that will have the following benefits:
Less time wasted
Fair and faster correction
The marking system requires certain rules:
The exam must be multiple-choice questions only
The project only works on windows
The drawbacks of the system:
Lack of equipment required in schools or universities
Lack of experience with this type of technology
Out of scope:
Linux computers
Essay exams

## Slide 8
Electronic Marking System
3.Testing
1.Plan System Design
4.Launching
2.Legal & Regulating
1.1.Project Proposal
2.1.Licensing
2.2.Government Permits
3.1.Design Review
3.3.Confirm Final Approval
3.2.1.Report on Integration of web security
1.2.Website Design
1.2.1.back end software
1.2.2.front end development
3.2.Progress Report
WBS

## Slide 9
Haneen | Nada | Nour | Menna | Shaimaa | Sohila | List of tasks
C | I | R | A | C | A | Plan System Design
A | C | I | R | A | C | Legal & Regulating
I | R | A | C | C | I | Testing
A | C | C | A | R | C | Launching

## Slide 10
0
A
1
Define Requirements
0
1
1
1
C
3
Legal & Regulating
4
2
6
1
D
2
Testing
2
1
3
8
O
13
Launching
8
5
13
FS = 0
1
B
2
Plan System Design
1
1
2
2
E
4
Project Proposal
3
2
5
3
G
4
Licensing
6
1
7
0
3
0
3
1
0
FS = 0
FS = 1
2
H
4
Design Review
3
2
5
FS = 0
2
F
5
Website Design
2
3
5
0
5
J
6
back end software
5
1
6
6
M
8
front end development
6
2
8
4
K
5
Government Permits
7
1
8
4
L
6
Confirm Final Approval
5
2
7
6
N
7
Report on Integration of web security
7
1
8
2
I
3
Progress Report
4
1
5
1
1
0
3
0
2
1
1
FS = 0
FS = 0
FS = 0
FS = 0
FS = 3
FS = 0
FS = 0
FS = 1
FS = 0
FS = 1
Network

## Slide 11
 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Define Requirements |  |  |  |  |  |  |  |  |  |  |  |  | 
Plan System Design |  |  |  |  |  | ◆ |  |  |  |  |  |  | 
Legal & Regulating |  |  |  |  |  |  |  |  |  |  |  |  | 
Testing |  |  |  |  |  |  |  |  |  |  | ◆ |  | 
Project Proposal |  |  |  |  |  |  |  |  |  |  |  |  | 
Website Design |  |  |  |  |  |  |  |  |  |  |  |  | 
Licensing |  |  |  |  |  |  |  |  |  |  |  |  | 
Design Review |  |  |  |  |  |  |  |  |  |  |  |  | 
Progress Report |  |  |  |  |  |  |  |  |  |  |  |  | 
back end software |  |  |  |  |  |  |  |  |  |  |  |  | 
Government Permits |  |  |  |  |  |  |  |  |  |  |  |  | 
Confirm Final Approval |  |  |  |  |  |  |  |  |  |  |  |  | 
front end development |  |  |  |  |  |  |  |  |  |  |  |  | 
Report on Integration of web security |  |  |  |  |  |  |  |  |  |  |  |  | 
Launching |  |  |  |  |  |  |  |  |  |  |  |  | 
GANTT CHART

## Slide 12
Resource - Constrained Schedule :
 |  |  |  |  |  |  |  |  |  |  |  |  |  | 2 | 0 | 1 | 0 | 1 | 2 | A
 |  |  |  |  |  |  |  |  |  |  |  |  | 2 |  | 0 | 2 | 1 | 1 | 2 | B
 |  |  |  |  |  |  |  |  |  |  |  | 2 | 2 |  | 3 | 6 | 1 | 2 | 2 | C
 |  |  |  |  |  |  |  |  |  |  |  |  | 2 |  | 1 | 3 | 1 | 1 | 2 | D
 |  |  |  |  |  |  |  |  |  |  | 2 | 2 |  |  | 1 | 5 | 2 | 2 | 2 | E
 |  |  |  |  |  |  |  |  |  | 2 | 2 | 2 |  |  | 0 | 5 | 2 | 3 | 2 | F
 |  |  |  |  |  |  |  |  |  |  | 2 |  |  |  | 3 | 7 | 3 | 1 | 2 | G
 |  |  |  |  |  |  |  |  |  |  | 2 | 2 |  |  | 1 | 5 | 2 | 2 | 2 | H
 |  |  |  |  |  |  |  |  |  |  |  | 2 |  |  | 2 | 5 | 2 | 1 | 2 | I
 |  |  |  |  |  |  |  |  | 2 |  |  |  |  |  | 0 | 6 | 5 | 1 | 2 | J
 |  |  |  |  |  |  |  |  |  | 2 |  |  |  |  | 3 | 8 | 4 | 1 | 2 | K
 |  |  |  |  |  |  |  |  | 2 | 2 |  |  |  |  | 1 | 7 | 4 | 2 | 2 | L
 |  |  |  |  |  |  | 2 | 2 |  |  |  |  |  |  | 0 | 8 | 6 | 2 | 2 | M
 |  |  |  |  |  |  |  | 2 |  |  |  |  |  |  | 1 | 8 | 6 | 1 | 2 | N
 |  | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  | 0 | 13 | 8 | 5 | 2 | O
- | - | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 6 | 8 | 10 | 6 | 2 | Resources Scheduled |  |  |  |  | 
10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | Resources Available |  |  |  |  | 
15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | SL | LF | ES | DUR | RES | ID

## Slide 13
Time – Phased budget :
 |  |  |  |  |  |  |  |  |  |  |  | 1 | 1 | Define Requirements | 1 | A
 |  |  |  |  |  |  |  |  |  |  | 3 |  | 3 | Plan System Design | 1 | B
 |  |  |  |  |  |  |  |  |  | 2.5 | 2.5 |  | 5 | Legal & Regulating | 2 | C
 |  |  |  |  |  |  |  |  |  |  | 5 |  | 5 | Testing | 1 | D
 |  |  |  |  |  |  |  |  | 2 | 2 |  |  | 4 | Project Proposal | 2 | E
 |  |  |  |  |  |  |  | 3 | 3 | 3 |  |  | 9 | Website Design | 3 | F
 |  |  |  |  |  |  |  |  | 8 |  |  |  | 8 | Licensing | 1 | G
 |  |  |  |  |  |  |  |  | 2 | 2 |  |  | 4 | Design Review | 2 | H
 |  |  |  |  |  |  |  |  |  | 3 |  |  | 3 | Progress Report | 1 | I
 |  |  |  |  |  |  | 4 |  |  |  |  |  | 4 | back end software | 1 | J
 |  |  |  |  |  |  |  | 1 |  |  |  |  | 1 | Government Permits | 1 | K
 |  |  |  |  |  |  | 1.5 | 1.5 |  |  |  |  | 3 | Confirm Final Approval | 2 | L
 |  |  |  |  | 2 | 2 |  |  |  |  |  |  | 4 | front end development | 2 | M
 |  |  |  |  |  | 1 |  |  |  |  |  |  | 1 | Report on Integration of web security | 1 | N
1 | 1 | 1 | 1 | 1 |  |  |  |  |  |  |  |  | 5 | Launching | 5 | O
1 | 1 | 1 | 1 | 1 | 2 | 3 | 5.5 | 5.5 | 15 | 12.5 | 10.5 | 1 | 60 | Weeks total |  | 
60 | 59 | 58 | 57 | 56 | 55 | 53 | 50 | 44.5 | 39 | 24 | 11.5 | 1 | Cumulative |  |  | 
13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | Budget | Task | DUR | ID

## Slide 14
Chart: Cumulative Baseline Budget
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Series 1 | 1 | 11.5 | 24 | 39 | 44.5 | 50 | 53 | 55 | 56 | 57 | 58 | 59 | 60

## Slide 15
Solutions | Risks
First, statistics and reviews must be made that measure the tolerance of all educational organizations individually, and then reports should be prepared that include percentage evaluations indicating the extent of the institution’s ability to implement the system, and set a certain percentage as a minimum for evaluation Institutions whose rating is equal to or more than the minimum have the ability to implement the system. Thus, the risk of lack of electronic competence in the institutions was avoided. Secondly, the state carries out development operations for all institutions that have not exceeded the minimum level and provides them with the necessary resources to be able in the near future to keep pace with technological development and follow up on those processes through specialized committees. | Not all educational organizations have the technological capacity to adopt an electronic correction system Therefore, many problems are expected if this system is applied to all educational organizations at once in Egypt
in this problem, the census and evaluation of employees in the same way as institutions will be useless, so it is better to do tests that measure their efficiency and assign trainers to train and teach employees modern technological methods in order to be able to deal with the system | Lack of efficiency in dealing with the system on the part of the employees in the institution

## Slide 16
Solutions | Risks
When applying the system in any institution, instructions are placed certain. For example: 1-Not to turn off or disconnect the electricity from the devices before making sure that the correction process occurred successfully. 2-Placing the data in storage devices such as CD and keeping those copies. | There are some problems that may occur during the electronic correction, for example, a power outage or a malfunction in the institution’s network, and we do not know a solution that will last for a short or long time, and perhaps during these malfunctions important data is lost